## Consolidation Plan
# | Consolidate | Rules | What changes (+ council fix) | Risk | Effort | When
Now | Fix lying comments (V67al) | - | Comments say dead V67al is active. Correct them. (the day-loser trap) | none | S | 1st
Now | Delete 5 junk files | - | .bak/.v13/.v24 + 2 game logs under src/ (untracked) | none | S | your OK
1 | DTF + maintenance: cache once | 5 | Compute DTF + maintenance once, cache it. Council: safest, ship first. | LOW | S | 1st batch
2 | Wave-win: one helper | 3 | One canWinAt() instead of 3. Extract-method only. | LOW | S | 1st batch
3 | 4th-shield block: one helper | 4 | One fourthShieldBlocked(); weights stay per-caller. | LOW | S | 1st batch
4 | Dead-search: drop hardcoded checks | 10 | Generic gate covers + dominates. COUNCIL FIX: V29.9/V29.11 'already-in-hand' guard is nested in this block - keep it; comment ONLY the dead -400 lines. | LOW* | M | needs the guard
5 | Move-blocks: 5 fixed levels | 9 | Clobber not add; fixes the +/-19998 double-fire. COUNCIL FIX: the +/-19998 is harmless; real risk is V37.1 -9999 clobbered at Safehouse. Ladder must rank HIDDEN_PATH_MANDATORY above STAY_AND_CRUSH. | MED | M | after tests
6 | Weapon-holder: one gate | 6 | COUNCIL FIX: V120 got the VADER fix TODAY - a careless merge brings the Vader bug back. Keep V120's detection; share ONLY the holder-count math; keep the 3 separate gates. Collides with other K-2's #1 fix - SYNC FIRST. | MED | M | sync K-2s
7 | Deploy occupancy: fold into site scorer | 8 | COUNCIL FIX: the +400 cap CHANGES a blocked deploy's score (not a no-op). Build per-rung boundary table first. The '3.3x route split' is cosmetic - lower priority. | MED | M | boundary table
8 | Reserve pulls: ONE scorer | 10+ | +6250 pile -> ~+2350. Council: V97-vs-V168(+5000) handling is correct - ACTIVATE pull must stay above +5000. All guards survive. Do LAST, alone, 1 build. | HIGH | L | LAST
Council review (2026-06-30):
Help agent (code-cited) + deepseek-r1:70b vetted. Alfred (Codex) unavailable - usage limit. Confidence ~85% if the 3 council fixes (moves 4/6/7) are applied; ~45% if shipped literally. Order: dead-code + 1/2/3 first, regression-test, #8 last and alone.