## Rando Issues
# | Problem | What I did | Status
1 | Vader never deploys (Hunt Down) | Fixed the V120 weapon-block so it no longer treats the 'Vader' character pull as the lightsaber weapon. Both bots. | DONE - deployed + committed (f664cc2ba)
2 | Weapons/devices pulled before characters | Nothing needed. The deploy walk already goes Locations - Characters - Weapons - Devices, so characters always deploy before weapons. What you saw was #1 in disguise. Your instinct was right. | HANDLED by structure - no change
3 | Force + cards pile up after turn 2 | Nothing needed - rides on #1 (once Vader/characters deploy, force isn't left to draw into hand). | AUTO - rides on #1
4 | A Good Friend / A Cunning Warrior waste their download | Fixed the ordering: a download that names a location you're HOLDING no longer outranks deploying that location from hand. So Rando deploys the location first, then the download can pull the epic event. Both bots. | DONE - deployed + committed (37c352d87)
5 | TDIGWATT Bug A: I'm Sorry never downloads interior CC sites (V177 false DEAD, 19 blocks; flip + income dead all game) | V177 CATEGORY RESCUE: before the -2000 block, consult validatePullFromSourceCard (the V67h path). WILL_SUCCEED = no block. Both bots. Same bug also blocked Piett's [any commander] search 27x. | DONE - verified LIVE 2026-07-02 (2 self-play games: rescue fired, site downloaded turn 1 both games)
6 | TDIGWATT Bug B: V29 BESPIN-FIRST taxes every character deploy -500 all game demanding Executor (71 fires; made every deploy a solo, T2 zero-deploy) | QUEUED. PREMISE CORRECTED by autopsy: objective does NOT forbid this deck's Executor (forbids only [Death Star II] one; deck runs 4_167 Dagobah). Real issue: release needs a ship AT Bespin, ships sat in Reserve all game. Fix design must change. | QUEUED - next up
7 | Suicide placements: V171 'battle THIS turn' +600 for a battle that was never legal (lone C-3PO, no presence); V170/V59 spy bonuses +750/+600 overrode the same eval's own 'not survivable 2v21' gate. Fed the 25 + 30 damage kill shots | NEW from 07-02 autopsy, adversarially verified. Fix shape: make V170/V59 respect the survivability gate already computed; gate V171 on a legally initiable battle. Not built. | NEW - awaiting Steve's pick
8 | V30 falsely says 'Executor in play' (getAllPermanentCards returns ALL zones incl. Reserve); V47 then hard-blocks Piett's ground deploy ~-10k. Benched Piett 3 of 4 turns | NEW from 07-02 autopsy, verified vs code+log. Fix shape: V30 must check in-play zones only. Not built. | NEW - awaiting Steve's pick
9 | Spread-over-concentrate landscape: fresh empty site (+800) always beats reinforcing a friend; nothing anywhere sees enemy power at ADJACENT sites; V113 exempts ability<3; V156 self-disabled on objective sites | NEW from 07-02 autopsy (structural). Fix would be an adjacent-enemy-threat term - needs boundary math + Steve's call on magnitudes. | NEW - discuss before building
10 | Search completes then takes NOTHING: T2 TDIGWATT pull declined Dark Deal (provably in Reserve); T1 Endor Shield admiral search also no-take | NEW from 07-02 autopsy, UNINVESTIGATED - no log line explains the decline. Needs a dedicated trace of the take-card selection step. | NEW - needs investigation
11 | Paid 3 Force to drain 1 with Battle Plan on board (2x, Audience Chamber, 07-04 game) | V189 NET-VALUE DRAIN GATE: engine cost query (getInitiateForceDrainCost), cost > drain = blocked. V140's false Battle-Plan waiver repaired in place. Both bots. UPDATED 2026-07-06: net -1 drains (pay 3 drain 2) now allowed when force after cost covers hand deployables + 2 move allowance, rechecked every decision; net -2 stays blocked. | BUILT v2 2026-07-06 - live verify pending
12 | Deployed starship Elis In Hinthra to Executor: Docking Bay (3x in 07-04 game) | V190: pull gate (starship-only fetch + no system/sector on table = block) + destination -1500 widened to ALL sites. Both bots. Sectors exempt pending Steve. Follow-up: make Rando deploy the system first. | BUILT 2026-07-04 - deploy + live verify pending
13 | Battle Order never deploys despite Rando controlling a battleground system + site all game (Verge/Scarif game, replay unli50oa1ur8bdux) | BUILT 2026-07-06: (1) V105/V117 4th-slot no longer hard-blocks every shield to prefer Battle Order when it's not on the menu (kills the 2760-fire deadlock; slot stays closed per Steve). (2) V51x2/V112 occupation checks unified onto engine occupiesBothTheaters (canSpot occupies+battleground_site/system) so gate agrees with V105. Both bots. Steve's call: 'just stop the spam'. | BUILT 2026-07-06 - deploy + self-play verify pending
14 | Battle Order should deploy turn 1-2 too when Rando occupies a battleground site + system (not just the turn-3 4th slot) | BUILT 2026-07-06: V51 both branches (shield + deploy, both bots) add +200 when occupiesBothTheaters (base 80 -> 280, beats auto-play 200), guarded shieldScore>-50 so V43/pacing still win. Occupy-only per Steve. Extended to 'battle plan'. Known gap: evaluateUnknown/V112 route not boosted. Self-play verify owed. | BUILT 2026-07-06 - deploy + self-play verify pending